## Warehouse
| Codes | Description | Durations | Predecessors
Gate | Start
Task | A | Agreement of the owner | (3, 4, 6) | Start
Task | B | Preparation of the ground | (1, 2, 4) | Start
Task | C | Order of materials | (1, 1, 3) | A
Task | D | Excavation | (1, 1, 3) | A, B
Task | E | Order of doors and windows | (1, 2, 4) | A
Task | F | Delivery of materials | (1, 2, 4) | C
Task | G | Concrete foundations | (1, 2, 4) | D, F
Task | H | Delivery of doors and windows | (8, 10, 12) | E
Task | J | Frame, roofs, walls | (3, 4, 6) | G
Task | K | Installation of doors and windows | (1, 1, 3) | H, J
Gate | End |  |  | K